Nuclear Power Station - Sizewell C

- This is a link to the EDF Energy website relating to Sizewell C

- This is a link to Sizewell C website

- This is a link to the Planning Inspectorate website with the decision on Sizewell C

- This is a link to the Sizewell C works tracker page to keep your parish up to date

Offshore wind farms

- This is a link to Scottish Power Renewables webpage covering East Anglia One North

- This is the link to the Planning Inspectorate website with the decision on EA ONE

- This is a link to Scottish Power Renewables webpage covering East Anglia TWO

- This is a link to the FIVE Estuaries website

Offshore electricity interconnectors

- This is a link to National Grid's webpage covering Lion Link

- This is a link to National Grid's webpage covering Sea Link

- This is a link to the Spring 2024 LionLink Newsletter circulated to parishes

Electricity transmission

- This is a link to National Grid's webpage covering Bramford to Twinstead reinforcement

- This is a link to National Grid's webpage covering Norwich to Tilbury electricity transmission

Solar energy

- This is a link to Sunnica energy farm website

- This is a link to the Planning Inspectorate website with the decision on Sunnica energy farm

- This is a link to the While Elm Solar Farm website

National Infrastructure Planning

- This is a link to National Infrastructure Planning website

Glossary

BESS = Battery Energy Storage System

DCO = Development Consent Order

DoR = Discharge of Requirement

EIA = Environmental Impact Assessment

NGET = National Grid Electricity Transmission

NGV = National Grid Ventures

NSIP = Nationally Significant Infrastructure Project

PINS = Planning Inspectorate

SCC = Suffolk County Council

Strategic Issues

On the 17 December 2025, the Council responded to a consultation from National Grid on

community benefits for the Bramford to Twinstead pylon line project, which may also have potential implications for other National Grid projects in Suffolk. https://www.suffolk.gov.uk/asset-library/community-benefits-response-bramford-to-twinstead-redacted.pdf

On the 16 January 2026 the Council responded to the Regional Energy Strategic Planning -Methodology Consultation setting out its concerns about the proposed governance arrangements and the need for greater transparency around future connections. The link to that letter is here: SCC -Regional Energy Strategic Plan Methodology Consultation Response 160126 Final

Proposed NSIP Projects in Suffolk  - Updates

(Projects in Alphabetical order)

East Anglia ONE North and TWO Offshore Wind Farms (Scottish Power Renewables (SPR))

Location: East Suffolk

East Anglia ONE North and TWO are proposals to create connections to a new substation at Friston via High Voltage Alternating Current undersea and underground cables.

Update (March 2026):

Current works include the construction of the haul road to support both the EA1N and EA 2 projects.

Works have also commenced at Kiln Lane substation in Friston with the Sustainable Urban Drainage (SuDs) basin excavation which will be used during the construction phases. Substation civils and construction works are expected to start in March 2026.

SCC Officers are continuing to discharge planning requirements for EA1N and 2, with those completed including, onshore cable stage, cable duct installation stage, footpath creation works at the substation and vegetation clearance for cables and the substation.

Substation design meetings were held throughout 2025, alongside public engagement events which were attended by the Parish Council and neighbouring residents.

SCC has submitted its significant concerns and objections to the developer declining to provide the footpath around the SuDS basin, which had been promised as a community benefit. The community are understandably upset regarding the situation, and SCC officers from Planning, Public Rights of Way and Floods have worked together and have successfully resolved this issue: SPR has now committed to the provision of the footpath around the SuDS Basin.

More information:

- Link to East Anglia ONE North's webpage: https://www.scottishpowerrenewables.com/pages/east_anglia_one_north.aspx

- Link to East Anglia TWO's webpage: https://www.scottishpowerrenewables.com/pages/east_anglia_two.aspx

- Link to the Suffolk County Council webpage on East Anglia ONE North: https://

- www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/east-anglia-one-north

- Link to the Suffolk County Council webpage on East Anglia TWO: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/east-anglia-two

- Link to the PINS webpage where all public documents relating to East Anglia ONE North can be found here: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN010077

- Link to the PINS webpage where all public documents relating to East Anglia TWO can be found here: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN010078

EcoPower Suffolk

Location: Mid Suffolk

An energy farm with solar PV and a co-located Battery Energy Storage System (BESS) and associated infrastructure which also includes a grid connection to the Yaxley National Grid substation. The project will consist of 600 hectares of solar panels spread across several sites, and a battery storage site to the south of Thrandeston.

Update (March 2026):

The Applicant has requested a Scoping Opinion from the Planning Inspectorate regarding the scope and level of detail of the information to be provided in the Environmental Statement relating to the EcoPower proposals.

The Scoping Opinion does not seek comments on the merits of the proposed development but on whether the Environmental Statement ensures it has effectively set out the potential impacts and likely significant impacts of the proposed development on the environment.

The Scoping Opinion was issued to consultation bodies identified by the Planning Inspectorate on 26 January 2026, and SCC reviewed documentation to provide a response by the deadline of 23 February 2026.

For the full news release see https://ecopowersuffolk.com/news

For more information on the statutory consultation see https://ecopowersuffolk.com/consultation-process/

More information:

- Link to EcoPower Suffolk's website: https://ecopowersuffolk.com

- Link to the PINS webpage where all public documents relating to EcoPower Suffolk can be found:

- https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN0110019

Five Estuaries Offshore Wind Farm

Location: Off East Suffolk coast / Essex

A wind farm proposed off the East Suffolk coast, with the landing point and onshore infrastructure proposed to be in Essex.

Update (March 2026):

The examination into the Five Estuaries Offshore Wind Farm concluded in March 2025. Secretary of State gave consent to the Five Estuaries DCO application on 17 December 2025.

Despite the efforts of officers, the Secretary of State did not consider that measures to enhance of the National Landscape were needed to satisfy updated legislation.

More information:

- Link to Five Estuaries' website: https://fiveestuaries.co.uk

- Link to Suffolk County Council's webpage on Five Estuaries: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/five-estuaries-offshore-windfarm

- Link to the PINS webpage where all public documents relating to Five Estuaries can be found:

- https://nationalinfrastructureconsenting.planninginspectorate.gov.uk/projects/EN010115

Helios Energy Park

Location: East Suffolk

Helios is a proposed energy farm consisting of ground mounted solar PV and battery energy storage system (BESS) in the locality of the consented but as yet unbuilt substation at Friston

(No update this issue)

Update from last issue (August 2025)

Deloitte, acting for the applicant of the proposed Helios Energy Farm, submitted a relevant representation in response to the Sea Link proposals, which brought the scheme into the public domain.

More Information:

- Link to Helios Energy Park relevant representation to Sea Link: nsip-

- documents.planninginspectorate.gov.uk/published-documents/EN020026-000593-Helios%20%20SEAL%20Link%20Relevant%20Representation%20230625_Redacted.pdf

- Link to Suffolk County Council's press release regarding the Helios proposals: https://www.suffolk.gov.uk/council-and-democracy/council-news/sea-link-paperwork-reveals-plans-for-large-solar-farm-near-friston

- Link to Suffolk County Council's webpage on Helios: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/helios-energy-park

LionLink

Location: East Suffolk

LionLink is the proposal by National Grid Ventures (NGV) for a subsea electricity link between Suffolk and the Netherlands, which will also connect with Dutch windfarms.

Update (March 2026):

The Applicant issued the Statutory Consultation for the LionLink proposals on 13 January with SCC technical officers providing input into the response to the Applicant.  On the 24th of February Suffolk County Council again called for National Grid to co-ordinate this project jointly with its sister project, SeaLink, to seek to reduce the impacts on communities. SCC is encouraging local communities to take part in the LionLink consultation. This is the last meaningful chance to help steer the project’s design, routing and purpose ahead of the application being lodged.

The full press release can be found here: https://www.suffolk.gov.uk/council-and-democracy/council-news/council-objects-to-lionlink-slamming-lack-of-coordination-and-fears-for-communities

More information:

- Link to LionLink’s National Grid website page: https://www.nationalgrid.com/national-grid-ventures/lionlink/about

- Link to Suffolk County Council's webpage on LionLink: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/lionlink

- Link to Suffolk County Council’s response to the non-statutory consultation: https://

- www.suffolk.gov.uk/asset-library/eurolink-non-statutory-consultation-scc-response1.pdf

- Link to Suffolk County Council’s response to the supplementary non-statutory consultation:

- https://www.suffolk.gov.uk/asset-library/LionLink-Supplementary-Non-Statutory-Consultation-SCC-response.pdf

- Link to the PINS webpage where all public documents relating to LionLink can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020033

North Falls Offshore Wind Farm

Location: Off East Suffolk coast / Essex

A wind farm proposed off the East Suffolk coast, with the landing point and onshore infrastructure proposed to be in Essex.

Update (March 2026):

Decision by the Secretary of State on the North Falls proposals is expected by April 2026 (decision was originally due in January 2026). Throughout the examination, SCC officers made representations regarding Landscape, Highways (particularly movement of Abnormal Indivisible Loads (AILs) and Skills and Economic Development impacts.

Following the end of the examination, SCC officers have responded to consultations from the Secretary of State regarding enhancement of the National Landscape. Officers have worked closely with the National Landscape Partnership’s team to formulate these responses.

More information:

- North Falls Website:  https://www.northfallsoffshore.com

- Link to the Suffolk County Council webpage on North Falls: https:/

- www.suffolk.gov.uk/planning-

- waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/north-falls-offshore-windfarm-scottish-and-southern-electricityrwe

- Link to the PINS webpage where all public documents relating to North Falls can be found:

- https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN010119

Norwich to Tilbury

Location: Babergh and Mid Suffolk

A proposal by National Grid Electricity Transmission (NGET) is to construct a new 400 kV electricity transmission line between Norwich Main Substation, Bramford Substation, the East Anglian Connection Node (near Lawford) and Tilbury Substation.

Update (March 2026):

The Examination has commenced for the Norwich to Tilbury DCO, with the Preliminary Meeting occurring on 10 February 2026 at Ipswich Town Football Club. This was immediately followed by an Open Floor Hearing for Interested Parties to share their perspectives and concerns regarding the Proposed Development.

A further two Open Floor Hearings in Norfolk and Essex, and an Issue Specific Hearing (focussing on alternatives) occurred within the same week. The Examination will run for a period of 6 months until 10 August 2026, with an Examining Authority panel of 5 inspectors.

Cllr Richard Rout has written to the relevant parish councils setting out the support that is

available to them see: https://www.suffolk.gov.uk/asset-library/norwich-to-tilbury-scc-letter-to-parishes-from-cllr-richard-rout-redacted.pdf

More information:

- Link to Norwich to Tilbury’s National Grid webpage: https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/norwich-to-tilbury

- Link to the Suffolk County Council webpage on Norwich to Tilbury: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/norwich-to-tilbury

- Link to Suffolk County Council's response to the Norwich to Tilbury non-statutory consultation:

- https://www.suffolk.gov.uk/asset-library/imported/scc-response-to-eag-informal-consultation-16-june.pdf

- Link to Suffolk County Council's response to the Norwich to Tilbury supplementary non-statutory

- consultation: https://www.suffolk.gov.uk/asset-library/scc-response-to-norwich-to-tilbury-non-stat-con-2.pdf

- Link to Suffolk County Council's response to the Norwich to Tilbury statutory consultation:

- https://www.suffolk.gov.uk/asset-library/scc-response-to-norwich-to-tilbury-statutory-consultation.pdf

- Link to Suffolk County Council's response to the Norwich to Tilbury targeted consultation: https://www.suffolk.gov.uk/asset-library/scc-n2t-targeted-con-2025-response-with-appendix.pdf

- Link to the PINS webpage where all public documents relating to Norwich to Tilbury can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020027

Suffolk Water Recycling, Transfer and Storage (SWRTS) Project

Location: East Suffolk and Mid Suffolk

Suffolk Water Recycling, Transfer and Storage is a Nationally Significant Infrastructure Project (NSIP) developed by Essex and Suffolk Water (part of Northumbrian Water), to construct an Advanced Water Recycling Plant and strategic network enhancements.

(No update this issue)

Update from last issue (November 2025)

A consultation opened on 27th October and closes on 10th December, and details can be found on the applicant’s website https://suffolkwaternetwork.co.uk/ourconsultation.html

More Information:

- Essex and Suffolk Water Project website: https://suffolkwaternetwork.co.uk/

- Suffolk County Council: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/suffolk-water-recycling

Sea Link

Location: East Suffolk

Sea Link is a proposal for a subsea, grid reinforcement link between Suffolk and Kent. Currently there is a proposed converter station near Saxmundham, connected by underground cables from a landing point between Aldeburgh and Thorpeness.  If the substation at Friston is not built under its existing consent as part of ScottishPower Renewables' East Anglia ONE North/TWO project, the substation will form part of the Sea Link proposals.

Update (March 2026):

The Sea Link Examination commenced on Wednesday November 5th and is ongoing until 5th May 2026. SCC has submitted requested submissions at each deadline, including The Local Impact Report, updated Statement of Common Ground, and the Principal Areas of Disagreement Summary Statement.

Further Issue Specific Hearings took place in late January at the Excel in London, with the planning team attending in person to represent SCC, supported by technical officers online. There, SCC made oral representations on a range of outstanding concerns, including working hours, traffic and transport, landscape, design, and cumulative effects. SCC has engaged with the Applicant outside of the examination process with further meetings to be arranged on outstanding issues.

This can be seen in full at https://www.suffolk.gov.uk/council-and-democracy/council-news/

suffolk-county-council-objects-to-sea-link-as-examination-begins-1

More information:

- Link to Sea Link’s National Grid website page: https://www.nationalgrid.com/the-great-grid-upgrade/sea-link

- Link to Suffolk County Council's Sea Link webpage: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/sea-link

- Link to Suffolk County Council's response to the Sea Link non-statutory consultation: https://www.suffolk.gov.uk/asset-library/sea-link-scc-response-non-statutory-consultation.pdf

- Link to Suffolk County Council's response to the Sea Link statutory consultation: https://www.suffolk.gov.uk/asset-library/scc-sea-link-statutory-consultation-response.pdf

- Link to Suffolk County Council's response to the Sea Link targeted consultation: https://

- www.suffolk.gov.uk/asset-library/Sea-Link-Targeted-Consultation-Response.pdf

- Link to Suffolk County Council's response to the Sea Link Grid pre-submission engagement:

- https://www.suffolk.gov.uk/asset-library/sea-link-pre-submission-engagement-response.pdf

- Link to the PINS webpage where all public documents relating to Sea Link can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020026

White Elm Solar Farm

Location: Mid Suffolk

White Elm Solar Farm is a proposed 675-acre solar farm, including battery storage, with a design capacity exceeding 50MW and located within the three parishes of Mendlesham, Wickham Skeith and Thwaite, approximately 7.5km north of Stowmarket.

(No update this issue)

Update from last issue (August 2025)

On 23 May 2025, Suffolk County Council received notification from the applicant of White Elm Solar Farm, Elmya Energy, that the development of the project had been paused indefinitely and the planned non-statutory consultation and associated public consultation events which were planned for 31 May and 4 June had been cancelled.

More information:

- Link to White Elm Solar Farm's Website: https://www.whiteelmsolarfarm.com

- Link to Suffolk County Council's statement on the pausing of White Elm Solar Farm: https://www.suffolk.gov.uk/council-and-democracy/council-news/statement-on-the-pausing-of-the-white-elm-solar-farm

- Link to Suffolk County Council's webpage on White Elm: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/white-elm-solar-farm

- Link to the PINS webpage where all public documents relating to White Elm Solar Farm can be

- found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN0110003

Consented NSIP Projects in Suffolk  - Updates

(Projects in Alphabetical order)

Bramford to Twinstead  Location: Babergh

This project proposal by National Grid Electricity Transmission (NGET) is to construct a new 400 kV power line between Bramford and Twinstead to reinforce the electricity transmission network.

Update (March 2026):

SCC officers are currently working on the Discharge of Requirements (DoR) for the Bramford to Twinstead scheme. Requirements for the main construction compound off the A134 have been discharged, and construction has commenced with the majority of the compound established.

Documents have been formally submitted for Stage 3 (overhead lines), Stage 4 (underground cables), and Stage 11 (works at Bramford substation).

The developer has undertaken a community consultation to seek views on what a community benefit fund should be used for, with a panel set to make decisions on initiatives from April 2026.

More information:

- Link to Bramford to Twinstead’s National Grid webpage: https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/bramford-twinstead

- Link to the Suffolk County Council webpage on Bramford to Twinstead: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/bramford-to-twinstead

- Link to the PINS webpage where all public documents relating to Bramford to Twinstead can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN020002

Sizewell C

Location: East Suffolk

Sizewell C is a 3.2-gigawatt EPR nuclear power station.

Sizewell C announced formal commencement on 15 January 2024.

Update (March 2026):

It has been two years since Sizewell C commenced their Associated Development Sites, Main Development Site and Ancillary Construction Area works. There has been significant progress on the Associated Development Sites, delivering the early infrastructure and mitigation required for the project. These are sites such as Northern and Southern Park & Rides, A12 Abnormal Intervisible Load Lay-by, Two Village Bypass, Sizewell Link Road, Pakenham Fen Meadow, and other local road improvement schemes. The Council continues to discharge requirements (DoR) and sign legal agreements for the technical designs for the local road mitigation schemes.

More information:

- Link to the Sizewell C website: https://www.sizewellc.com

- Link to Suffolk County Council's webpage on Sizewell C: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/sizewell-c-nuclear-power-plant

- Link to the PINS webpage where all public documents relating to Sizewell C can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN010012

- Link to Government announcement of final investment decision: https://www.gov.uk/government/news/sizewell-c-gets-green-light-with-final-investment-decision

Sunnica Energy Farm

Location: West Suffolk

A proposed 630MW solar farm including battery energy storage systems across approximately 1,041 hectares (2,573 acres) of West Suffolk and East Cambridgeshire.

Update (March 2026):

In January, the Council responded to the Non-Material Change application submitted by the Applicant to amend the Development Consent Order as made by the Secretary of State. The change concerned a revision to the Order Limits of the Scheme to facilitate the Point of Connection, namely,

to include a new parcel of land that has been developed upon at Burwell Substation since the Scheme was examined. The decision on the application, which rests upon the Secretary of State, has yet to be made. The Council is also in discussions with the Applicant regarding progress towards the Discharge of Requirements. The process is anticipated to take two stages: with the initial stage starting towards the end of 2026 (covering matters not dependent on the detailed design of the Scheme), and the detailed stage starting around mid-2027 (covering matters which will follow the detailed design of the Scheme).

More information:

- Link to Sunnica’s website: https://sunnica.co.uk

- Link to Suffolk County Council's webpage on Sunnica: https://www.suffolk.gov.uk/planning-waste-and-environment/major-infrastructure-projects-including-nsips/nsips-in-suffolk/sunnica-energy-farm

- Link to the PINS webpage where all public documents relating to Sunnica can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN010106

Other Consented NSIPs

The following NSIPs in Suffolk have currently no significant updates to report:

- Drax (formerly Progress Power) at Eye Airfield: Consented. Construction is ongoing. The applicant is in correspondence with the government regarding making further changes to the Development Consent Order for this Project, which have implications for the access arrangement for this site. Further information can be found at: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN010060

- Gull Wing Bridge: Thousands of Lowestoft residents made history on 7 September 2024 as they walked, wheeled and drove for the first time across the town’s new, world-leading and unique Gull Wing bridge. The civic opening ceremony took place on Tuesday 19 November 2024.

- SPR - East Anglia ONE and THREE: Both are consented. East Anglia ONE (EA1) is complete; East Anglia THREE (EA3) is under construction. EA3 Update March 2026 - Installation of electrical equipment is almost complete on site and commissioning activities are underway. EA3 substation is estimated to be completed by Spring 2026.

In addition, there is the possibility in the medium term of additional NSIPs, in relation to hydrogen infrastructure, water reservoirs, data centres, energy generation and potentially, in the longer term, further National Grid infrastructure. Future newsletters will update on further developments.

Neighbouring NSIP Project Updates

Parish and town councils located near county borders should stay informed about any proposed Nationally Significant Infrastructure Projects (NSIPs).

East Pye Solar

Location: South Norfolk

The East Pye Solar proposals include the construction, operation, maintenance, and decommissioning of ground-mounted solar PV arrays and associated development, including a Battery Energy Storage System (BESS), in the area of Long Stratton, South Norfolk

Update (March 2026):

SCC made responses to non-statutory and statutory consultations regarding potential concerns around traffic and transport, including AILs and potential overlap with other NSIPs in Mid Suffolk, and socioeconomics.

The application is expected to be submitted soon Q1/Q2 2026

More information:

- Link to East Pye Solar's webpage: https://www.eastpyesolar.co.uk/

- Link to the PINS webpage where all public documents relating to East Pye Solar can be found: https://national-infrastructure-consenting.planninginspectorate.gov.uk/projects/EN0110014

Kingsway Solar Farm

Location: East Cambridgeshire

A proposed 500MW solar farm including battery energy storage systems across approximately 1,246 hectares (3,079 acres) of East Cambridgeshire.

(No update this issue)

Update from last issue (November 2025)

Between 17 September and 29 October 2025, Kingsway Solar Farm undertook a Statutory Consultation on their scheme (proposed to be located near Balsham, Cambridgeshire). The scheme is proposed to connect to Burwell Substation and therefore will interact with Sunnica Energy Farm.

As such, Suffolk County Council responded to the Statutory Consultation with respect to cumulative impact: SCC Kingsway Solar Farm - Statutory Consultation Response (Oct 2025)

This proposed solar farm has recently hosted a Statutory Consultation, between 17 September and 29 October 2025, and would be located across three land parcels (near Balsham, Cambridgeshire).

Whilst the development is proposed to be wholly in Cambridgeshire, the proposals for overhead lines to connect into the 400kv Burwell Substation tightly align with the Suffolk border near Newmarket.

The proposals will also interact with the Sunnica Energy Farm order limits at the Burwell Substation. The concerns regarding Suffolk therefore will focus on cumulative impacts, and landscape and visual matters.

Further information, including an interactive map of the proposed development can be found on the Applicant’s website - https://kingswaysolarfarm.co.uk/the-scheme/.

Tarchon Interconnector

Location: Tendering District / Essex

The proposals consist of an interconnector between Essex and Germany with a capacity of 1.4 GW. A converter station will be located nearby the proposed East Anglia Connection Node in Lawford which serves as the project's connection point to the Grid. Underground cabling will make landfall south of Harwich.

Update (March 2026):

The project promoter currently expects to submit the application to the Planning Inspectorate in 2027.

SCC has submitted its response to non-statutory consultation in May 2025. Whilst the project is still in the early stages, SCC conveyed key concerns including the impacts of the converter station on the Dedham Vale National Landscape, compliance with the new duty to seek to further the purposes of National Landscapes and the cumulative effects of the project in combination with other projects connecting to the EACN and Norwich to Tilbury.

More Information:

- Link to the Tarchon Interconnector's webpage: https://www.tarchonenergy.net

Tasway Energy Park  Location: South Norfolk

The Tasway Energy Park proposals consist of large-scale solar PV with battery energy storage system (BESS) along with associated infrastructure including cabling and an onsite substation.

Update (March 2026):

The project promoter confirmed on Friday 12th December that this project has now been paused until  further notice.

More Information:

- Link to the Tasway Energy Park website: https://www.taswayenergypark.co.uk

- Link to the South Norfolk and Broadland webpage on Tasway: https://

- www.southnorfolkandbroadland.gov.uk/planning/nationally-significant-infrastructure-projects/tasway-energy-park-aukera-energy

NSIP Mapping

Screenshot of the

NSIP map on the

SCC website

Suffolk County Council have produced a web-based public-facing interactive map to display NSIPs in the county of Suffolk and neighbouring districts. Where Suffolk County Council have received written permission, the Council has published the Order Limits of each proposal. Where Suffolk

County Council has been unsuccessful in obtaining written permission, point data at the centre of the NSIP has been provided. Small-scale (non-NSIP) ground-mounted solar farms are also shown as yellow dots.

Nationally Significant Infrastructure Projects (NSIPs) throughout their lifecycle are displayed. This includes those in Pre-Application, Examination, Granted Consent, Construction, and Operational.

You can access the map via the SCC Website or via this link: https://experience.arcgis.com/

experience/b8e2edd5fbcd4c75b74aa38da7e710ed

The mapping tool includes several utility functions, including ability to tap or click on each NSIP to understand its infrastructure further, and a bookmark selector which allows you to scroll through a carousel to re-focus the map on each NSIP (with a brief description).

Disclaimer: Please note that the map is designed to provide members of the public with access to illustrative and indicative location-based data for information purposes only. Every effort has been made to ensure that the information displayed is accurate and regularly updated. The database is currently in development and datasets may be added or removed during this process.